## Slide 1: ENERGY PERFORMANCE REGISTER Highlight Report
RISKS |  |  |  | 
Risk | Mitigation Taken | Future Mitigations | Owner | RAG
EPB solution is not delivered within the required timescales and/or the migration process is delayed. | Planning, objectives for BETA preparation assumes a “No Big Bang“ approach, i.e. the critical service provision is implemented first and other less critical work after Dec 2019. | On-going planning work and engagement with delivery partners(GDS, suppliers, stakeholders and users, procurement, legal) to ensure validation of planning assumptions and in mitigating key delivery risks as part BETA and Transition planning. Recruitment of experienced Transition Manager to validate and manage Exit and Transition Plans/Strategies develop Project Transition and Exit Strategies; Develop Stakeholder and Communication Plan and management of key stakeholders and users necessary to validate new service and mitigation of delivery risks. | Chandru | R
Project does not secure GDS approval for Alpha and BETA and LIVE Service Phases by scheduled target/baseline dates, therefore all other key Milestones and implementation is delayed. | Established single point of contact with MHCLG Digital and GDS team to provide technical and service standard advise in a timely manner and have procured technical capability to inform on Alpha and BETA assessment. Alpha senior delivery partner and MHCLG delivery partner (Paul Downey) are experienced GDS advisors(have worked for them or have implemented GDS compliant services previously and successfully) | Maintain regular engagement with GDS during the Alpha and BETA including throughout the project. Ensure agile process is planned in accordance with GDS Service Standards and 18 Point Plan on Technology Code. | Chandru | A/R
EPB Commercial and Financial Model experiences funding shortfalls and becomes unsustainable. | Some commercial assessment undertaken by PwC focussing on the future commercial arrangements(not Concession Model, but fixed cost model) but detailed financial and commercial options needs to be developed. | Undertake further financial and economical analysis by commercial experts to calculate a sustainable financial and commercial operating model going forward to mitigate key economical and EPB income risks utilising previous and current data in conjunction with HMT recommendations. | Chandru | A/R
ESCALATED ITEMS FROM PROJECT
Delivery Confidence for project is improving however, very difficult to assess technical complexities to be managed within tight timescales and confidence that new service being implemented by end 2019/20: Technical and Data Migration complexities could impact timetable; Securing competent and reliable supplier to build service Future commercial and Financial Model agreed. developed and
ISSUES |  |  | 
Issue | Corrective Actions | Owner | Priority
Development of EPB Register future funding and commercial model. | Actions taken: Some commercial assessment undertaken by PwC focussing on the future commercial arrangements(not Concession Model, but fixed cost model) but detailed financial and commercial options needs to be developed to support sustainability case in OBC and BETA(tender) preparation. Future actions: Undertake further financial and economical analysis by commercial experts to calculate a sustainable financial and commercial operating model going forward to mitigate key economical and EPB income risks utilising previous and current data in conjunction with HMT recommendations | Debbie Brown | Medium or High
LEVEL 0 MILESTONES |  |  |  | 
Milestone | Baseline | Forecast | Status | Comments
Outline Business Case Approval from ISC in April. | May-10 | May-19 | A | 60% of the OBC has been drafted , further narrative needs to be included around commercial, financial and procurement approach(utilizing Alpha technical and business outputs)
Alpha Outputs; GDS Service Standard Assessment and Spending Control Approved | Apr-19 | Apr-19 | A | Initial Alpha analysis indicate that Digital Transformation of current Register does not indicate too many technical complexities, but this will be validated throughout the Alpha Phase. Working closely with GDS to mitigate potential issue/risk to secure approval.
BETA Requirements and DOS ITT finalised for Publishing to Market | Apr-19 | Apr-19 | A | This will be worked through with Alpha Team and all DOS ITT will be prepared alongside Alpha Outputs.
Ministerial Approval on BETA(approval to go to market) | May-19 | May-19 | A | Preparation alongside work on OBC and Alpha Outcomes /GDS approval.
FORWARD LOOK (next 4 weeks)
Key Activities: Selection of Business Analyst and prepare OBC for ISC approval (April) Review Exit Plan and Transition Arrangements with Landmark(identify and agree contractual Assistance provisions) Review Data Migration with Alpha team(to identify additional work for Landmark) as necessary for smooth transition Arrange Prior Notice and pre-Engagement with potential suppliers interested in BETA opportunity(with support from alpha) Visit Landmark with alpha team to assess technical build of the current service Develop and finalise future commercial and financial arrangement for operating new service/supplier Upcoming Submissions: EPB Lodgement Fees for 2019/20(leave unchanged)? Ministerial Submission for BETA Publication(April 2019) Ministerial Submission on EPB Register Contract Award
OVERALL PROGECT DELIVERY CONFIDENCE | A/R
KEY ACHIEVEMENTS (last 4 weeks)
Key Activities: Contract Extension agreed up to Nov 2019 with options to extend and secured savings of £500K+ Maintained continuity of service during re-build and transition Recruited Alpha supplier and work underway(10 weeks) Key stakeholder/User consultation and validation commenced for Alpha Agreed date for GDS Service Standard Assessment(April) Republished BA specification to support OBC update by April Agreed a way forward on EPB Fees amendments for 2019/20 Reviewing Exit and Transition Plans with Landmark. Key Milestones and Critical Path to deliver: To maintain Service Continuity during Transition -Landmark service extension finalised (Dec 2018 – Jan 2019) Complete Alpha work and secure GDS Approval (March/April 2019) OBC finalised and approved by ISC(April 2019) Ministerial Approval Secured (April 2019) BETA(procurement documents ) prepared and readiness for DOS ITT publication (March 2019) BETA Publication to Digital Market Place ( 2 weeks in April 2019) BETA Evaluation and Selection of Preferred Supplier(May 2019) BETA Supplier Selected(Early un 19) BETA Build(Private BETA) - (Early June 2019) Private → Public Beta assessment (Mid Aug 2019) Beta build ends (Early Dec 2019) Beta → Live assessment(Mid Dec 2019) Dual running/staged switchover - January → March 2020
Reporting Period: Dec 2018 to 30th January 2019