## Slide 1
EPB Ratification
Milestone complete
Milestone at risk, not on critical path
Milestone at risk and on critical path
Milestone on track
External milestone
Milestone status unknown
Key to Milestones
Dependency
Milestone slippage
Building Safety Portfolio: EPB Registers Project (POAP)
V0.02 16 January 2019
Official
2019
2020
EU EXIT
Develop EPB Reformed Legislation
Brexit and Policy
Ministerial Decisions
ISC/Finance Clearance
GDS Clearance
Business Case Approval
Alpha
Procurement DOS ITT Phase
Exit & Transition
New Service Delivery & Preparations
Discovery P2
Alpha Outputs
Contract Extension Agreed
Contractual EXIT Assistance obligations being reviewed
Live Service
Alpha Supplier Recruited
OBC Update
Discovery Complete
Alpha Assessment (2 April)
Beta – Live Assessment
OBC to ISC
(May)
2018
Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Contract Extension
Discovery
Agree further contract extension with Landmark
Beta
Private Beta
DOS ITT
Public Beta
Ministerial sign-off
(June)
Project Board
Project Board
(April)
Private to Public Assessment
MHCLG combined Exit Strategy Development
Agree Exit Plans
Market Sounding
DOS ITT Requirements Capture
New Supplier Engaged
Award Contract
Evaluation of
Tenders
PIN Notice
Period
Landmark Exit Plans being reviewed and service and design documentation being gathered
Final Business Case/Benefit tracking
Agile EPB System Build, UAT and Validation of new service
CURRENT EXTENSION EXPIRES
Transition Manager Recruited
Develop Transition Stakeholder and Communication Plans
Transition Management and Assurance Tracking
Agree further extension?
Legacy Data Migration Strategy and risk mitigation plans